## LocalPlanReview2040Timetable
reference | plan | plan-event | event-date | entry-date | actual-date | notes
SH-LPR-2040-publish-notice-intention-commence | surrey-heath-local-plan-review-2040 | publish-notice-intention-commence | 25/06/2026 | 14/09/2026
SH-LPR-2040-scoping-consultation-start | surrey-heath-local-plan-review-2040 | scoping-consultation-start | 14/09/2026 | 14/09/2026 |  | This consultation seeks views from stakeholders on the scope of the Local Plan and how they wish to be engaged in the plan-making process.
SH-LPR-2040-scoping-consultation-end | surrey-heath-local-plan-review-2040 | scoping-consultation-end | 19/10/2026 | 14/09/2026
SH-LPR-2040-gateway-1-self-assessment | surrey-heath-local-plan-review-2040 | gateway-1-self-assessment | 26/10/2026 | 14/09/2026 |  | This formally marks the start of the 30 month plan-making process and is a summary of work carried out to get ready to start the formal plan-making process.
SH-LPR-2040-plan-content-evidence-consultation-start | surrey-heath-local-plan-review-2040 | plan-content-evidence-consultation-start | 2027-01-06 | 14/09/2026 |  | This consultation will seek views on the proposed vision, spatial strategy options and a summary of the evidence gathered to date. It may seek views on policy wordings. The consultation will last for a minimum 6 weeks.
SH-LPR-2040-plan-content-evidence-consultation-end | surrey-heath-local-plan-review-2040 | plan-content-evidence-consultation-end | 14/07/2027 | 14/09/2026
SH-LPR-2040-gateway-2-advice-sought | surrey-heath-local-plan-review-2040 | gateway-2-advice-sought | 2027-01-09 | 14/09/2026 |  | An appointed assessor from the Planning Inspectorate will review progress on the Plan and provide observations and recommendations to the Council.
SH-LPR-2040-proposed-plan-consultation-start | surrey-heath-local-plan-review-2040 | proposed-plan-consultation-start | 2028-03-04 | 14/09/2026 |  | This final formal consultation will seek views on a full draft plan and policies map. The consultation will last for a minimum 8 weeks.
SH-LPR-2040-proposed-plan-consultation-end | surrey-heath-local-plan-review-2040 | proposed-plan-consultation-end | 29/05/2028 | 14/09/2026
SH-LPR-2040-gateway-3-advice-sought | surrey-heath-local-plan-review-2040 | gateway-3-advice-sought | 2028-01-08 | 14/09/2026 |  | An appointed assessor from the Planning Inspectorate will decide whether the Plan is ready for submission based on prescribed requirements on legal compliance and the proposed submission documents.
SH-LPR-2040-examination-submitted | surrey-heath-local-plan-review-2040 | examination-submitted | 2028-02-10 | 14/09/2026 |  | Subject to passing Gateway 3 the Plan and supporting documents will be submitted to the Secretary of State for Examination.
SH-LPR-2040-adopted | surrey-heath-local-plan-review-2040 | adopted | 26/04/2029 | 14/09/2026 |  | Once adopted, the Plan will form part of the statutory Development Plan for the West Surrey Council area.